## Ark1
		WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5
20.apr	21.apr	23.apr	24.apr	25.apr			28.apr	29.apr	30.apr	01.mai	02.mai			05.mai	06.mai	07.mai	08.mai	09.mai			12.mai	13.mai	14.mai	15.mai	16.mai			19.mai	20.mai	21.mai	22.mai	23.mai		25.mai
M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
Gantt chart & planing document
	Research
			Functional spec

				Deliver
				Target Audiance
		User stories					Skeching
		card sorting					Build Prototype
				Deliver
				Structure
				HTML/CSS mobil device
			thinking about					HTML/cssdesktop&tablet
			target audiance					Colorpalett					Javascript
			moodboard					Choosing Images					HTML/CSS mobil device
				Font					HTML/cssdesktop&tablet
				Choose API					Javascript					Testing in browsers
				Summary					Summary					Writing report
				of week					of week					write if needed
				Summary					Deliver
				of week

				Summary
				of week
				Fixing bugs
Week Starting the planning process with creating a Gantt chat to get an overview over the next weeks. After that I will start on user stories and to create Function specifications out of those. Including epics and features. Through the user stories I will start thinking about the target audience for the website. I will also start on researching a few web sites to get an overview on what is needed for this kind of theme. Every Friday I will write a sort summery of the week, how it went and what may have going to wrong to make it easier for me to write the report at the end. / Deliver function specifications and planning document					Week I will decide the final audience and start on building the Prototype. Starting the process with choosing WCAG colorpalett fonts, and images to use. Also Deciding an API. / Deliver prototype on Sunday.					Week 3 I will star with deciding on what elements I will use JavaScript for. Then I will start building the structure/ grid of the website. Including colors and the rest of the set up. I will star creating the mobile friendly version. I will also write down question’s I eventually have for teachers.
				Week 4 Keep working on the website and writing summary					Week 4 That week I start testing in different browsers and devices, hopefully I can start with that at the end of week four, so I have more time to fix bugs. When all that is done, I start on the report buy using my notes to make it easier to remember. / Deliver Final product on Sunday.
				Fixing bugs